## Sheet1
[8 empty] | PROGRESS : | 1 | 1
2
No. | Module | No Tiket | Test Case | APPS | Sprint | Scenario Type | Test Case Description | Action | Expected result | Status |  | Data | PIC | Date | Remarks | TEST NODES
[10 empty] | Passed | Failed |  |  |  |  | Endpoint | Request Sample | Expected Responses | Curl Sample
MODULE: ACCESS
1 | access |  | Get Role Access | API | 1 | positif | getting Role Access | GET /api/v1/master/roles/1/access | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1/access | - | {"status":200} | curl -X GET "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1/access"
2 | access |  | Update Role Access | API | 1 | positif | updating Role Access | POST /api/v1/master/roles/1/access | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1/access | {"menu_ids":[1,2]} | {"status":200} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1/access" -H "Content-Type: application/json" -d "{\"menu_ids\":[1,2]}"
MODULE: AUTH
1 | auth |  | User Registration | API | 1 | positif | user Registration | POST /api/v1/auth/register | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/auth/register | {"email":"test@example.com","password":"password123"} | {"status":201,"message":"Created"} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/auth/register" -H "Content-Type: application/json" -d "{\"email\":\"test@example.com\",\"password\":\"password123\"}"
2 | auth |  | User Login | API | 1 | positif | user Login | POST /api/v1/auth/login | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/auth/login | {"username":"admin","password":"password"} | {"status":200,"message":"OK"} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/auth/login" -H "Content-Type: application/json" -d "{\"username\":\"admin\",\"password\":\"password\"}"
MODULE: BRANCH
1 | branch |  | Search Branch | API | 1 | positif | searching Branch | POST /api/v1/master/branches/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | branch |  | Create Branch | API | 1 | positif | creating Branch | POST /api/v1/master/branches | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/branches | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/branches" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | branch |  | Update Branch | API | 1 | positif | updating Branch | PUT /api/v1/master/branches/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | branch |  | Delete Branch | API | 1 | positif | deleting Branch | DELETE /api/v1/master/branches/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/branches/1"
MODULE: CABANG
1 | cabang |  | Search Cabang | API | 1 | positif | searching Cabang | POST /api/v1/master/cabang/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | cabang |  | Create Cabang | API | 1 | positif | creating Cabang | POST /api/v1/master/cabang | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | cabang |  | Update Cabang | API | 1 | positif | updating Cabang | PUT /api/v1/master/cabang/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | cabang |  | Delete Cabang | API | 1 | positif | deleting Cabang | DELETE /api/v1/master/cabang/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/cabang/1"
MODULE: CARGO
1 | cargo |  | Search Cargo | API | 1 | positif | searching Cargo | POST /api/v1/master/barang/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | cargo |  | Create Cargo | API | 1 | positif | creating Cargo | POST /api/v1/master/barang | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/barang | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/barang" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | cargo |  | Update Cargo | API | 1 | positif | updating Cargo | PUT /api/v1/master/barang/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | cargo |  | Delete Cargo | API | 1 | positif | deleting Cargo | DELETE /api/v1/master/barang/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/barang/1"
MODULE: COMPANY
1 | company |  | Search Company | API | 1 | positif | searching Company | POST /api/v1/master/company/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/company/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/company/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | company |  | Create Company | API | 1 | positif | creating Company | POST /api/v1/master/company | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/company | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/company" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | company |  | Update Company | API | 1 | positif | updating Company | PUT /api/v1/master/company/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/company/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/company/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | company |  | Delete Company | API | 1 | positif | deleting Company | DELETE /api/v1/master/company/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/company/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/company/1"
MODULE: CUSTOMER
1 | customer |  | Search Customer | API | 1 | positif | searching Customer | POST /api/v1/master/customer/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | customer |  | Create Customer | API | 1 | positif | creating Customer | POST /api/v1/master/customer | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/customer | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/customer" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | customer |  | Update Customer | API | 1 | positif | updating Customer | PUT /api/v1/master/customer/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | customer |  | Delete Customer | API | 1 | positif | deleting Customer | DELETE /api/v1/master/customer/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/customer/1"
MODULE: DERMAGA
1 | dermaga |  | Search Dermaga | API | 1 | positif | searching Dermaga | POST /api/v1/dermaga/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | dermaga |  | Create Dermaga | API | 1 | positif | creating Dermaga | POST /api/v1/dermaga | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/dermaga | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/dermaga" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | dermaga |  | Update Dermaga | API | 1 | positif | updating Dermaga | PUT /api/v1/dermaga/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | dermaga |  | Delete Dermaga | API | 1 | positif | deleting Dermaga | DELETE /api/v1/dermaga/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/dermaga/1"
MODULE: DOCK
1 | dock |  | Search Dock | API | 1 | positif | searching Dock | POST /api/v1/master/dock/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | dock |  | Create Dock | API | 1 | positif | creating Dock | POST /api/v1/master/dock | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/dock | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/dock" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | dock |  | Update Dock | API | 1 | positif | updating Dock | PUT /api/v1/master/dock/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | dock |  | Delete Dock | API | 1 | positif | deleting Dock | DELETE /api/v1/master/dock/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/dock/1"
MODULE: EQUIPMENT
1 | equipment |  | Search Equipment | API | 1 | positif | searching Equipment | POST /api/v1/master/equipment/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | equipment |  | Create Equipment | API | 1 | positif | creating Equipment | POST /api/v1/master/equipment | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | equipment |  | Update Equipment | API | 1 | positif | updating Equipment | PUT /api/v1/master/equipment/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | equipment |  | Delete Equipment | API | 1 | positif | deleting Equipment | DELETE /api/v1/master/equipment/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/equipment/1"
MODULE: MENU
1 | menu |  | Search Menu | API | 1 | positif | searching Menu | POST /api/v1/master/menus/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | menu |  | Create Menu | API | 1 | positif | creating Menu | POST /api/v1/master/menus | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/menus | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/menus" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | menu |  | Update Menu | API | 1 | positif | updating Menu | PUT /api/v1/master/menus/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | menu |  | Delete Menu | API | 1 | positif | deleting Menu | DELETE /api/v1/master/menus/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/menus/1"
MODULE: PELABUHAN
1 | pelabuhan |  | Search Pelabuhan | API | 1 | positif | searching Pelabuhan | POST /api/v1/master/pelabuhan/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | pelabuhan |  | Create Pelabuhan | API | 1 | positif | creating Pelabuhan | POST /api/v1/master/pelabuhan | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | pelabuhan |  | Update Pelabuhan | API | 1 | positif | updating Pelabuhan | PUT /api/v1/master/pelabuhan/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | pelabuhan |  | Delete Pelabuhan | API | 1 | positif | deleting Pelabuhan | DELETE /api/v1/master/pelabuhan/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/pelabuhan/1"
MODULE: REFERENCE
1 | reference |  | Search Reference | API | 1 | positif | searching Reference | POST /api/v1/master/reference/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | reference |  | Create Reference | API | 1 | positif | creating Reference | POST /api/v1/master/reference | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/reference | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/reference" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | reference |  | Update Reference | API | 1 | positif | updating Reference | PUT /api/v1/master/reference/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | reference |  | Delete Reference | API | 1 | positif | deleting Reference | DELETE /api/v1/master/reference/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/reference/1"
MODULE: ROLE
1 | role |  | Search Role | API | 1 | positif | searching Role | POST /api/v1/master/roles/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | role |  | Create Role | API | 1 | positif | creating Role | POST /api/v1/master/roles | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | role |  | Update Role | API | 1 | positif | updating Role | PUT /api/v1/master/roles/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | role |  | Delete Role | API | 1 | positif | deleting Role | DELETE /api/v1/master/roles/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/roles/1"
MODULE: TERMINAL
1 | terminal |  | Search Terminal | API | 1 | positif | searching Terminal | POST /api/v1/master/terminals/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | terminal |  | Create Terminal | API | 1 | positif | creating Terminal | POST /api/v1/master/terminals | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | terminal |  | Update Terminal | API | 1 | positif | updating Terminal | PUT /api/v1/master/terminals/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | terminal |  | Delete Terminal | API | 1 | positif | deleting Terminal | DELETE /api/v1/master/terminals/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/terminals/1"
MODULE: USER
1 | user |  | Get Profile | API | 1 | positif | getting Profile | GET /api/v1/users/profile | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/users/profile | - | {"status":200} | curl -X GET "http://dev-tuks-api.ilcs.co.id/api/v1/users/profile"
2 | user |  | Search Users | API | 1 | positif | searching Users | POST /api/v1/master/users/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/users/search | {"filter":{}} | {"status":200} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/users/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
MODULE: VESSEL
1 | vessel |  | Search Vessel | API | 1 | positif | searching Vessel | POST /api/v1/master/vessel/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | vessel |  | Create Vessel | API | 1 | positif | creating Vessel | POST /api/v1/master/vessel | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | vessel |  | Update Vessel | API | 1 | positif | updating Vessel | PUT /api/v1/master/vessel/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | vessel |  | Delete Vessel | API | 1 | positif | deleting Vessel | DELETE /api/v1/master/vessel/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/vessel/1"
MODULE: WAREHOUSE
1 | warehouse |  | Search Warehouse | API | 1 | positif | searching Warehouse | POST /api/v1/master/warehouse/search | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/search | {"filter":{}} | {"status":200,"data":[]} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/search" -H "Content-Type: application/json" -d "{\"filter\":{}}"
2 | warehouse |  | Create Warehouse | API | 1 | positif | creating Warehouse | POST /api/v1/master/warehouse | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse | {"name":"test"} | {"status":201} | curl -X POST "http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse" -H "Content-Type: application/json" -d "{\"name\":\"test\"}"
3 | warehouse |  | Update Warehouse | API | 1 | positif | updating Warehouse | PUT /api/v1/master/warehouse/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/1 | {"name":"updated"} | {"status":200} | curl -X PUT "http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/1" -H "Content-Type: application/json" -d "{\"name\":\"updated\"}"
4 | warehouse |  | Delete Warehouse | API | 1 | positif | deleting Warehouse | DELETE /api/v1/master/warehouse/1 | success | 0 | 0 |  | Sofyan | 2026-04-23 |  | http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/1 | - | {"status":200} | curl -X DELETE "http://dev-tuks-api.ilcs.co.id/api/v1/master/warehouse/1"